## Product Backlog
Building Counstruction
Project Name | Building Counstruction
User Story | Plan for a building construction project involves breaking the overal project into 8 manageable phases. With each sprint lasting around 2 weeks. The project will be devided into tasks such as site preparation. Foundation work, framing, electrical, plumbing installation, fininshing and inspection.
Project Manager | XYZ
Duration | 8 months
Start date | 2024-01-06
End Date | 28/2/2025
Sprint Duration | 2 Weeks Per Sprint
Sprint Goal | Complate critical counstruction milestones to ensure steady progress toward the building's completion
Budget | 20,00,000/-

## Sprint 1
SPRINT 1 :
| USER STORY | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY
| Land Clearing and Grading | D 1 | 2024-01-06 | 2024-06-06 | 5 | Complete | High
| Excavation of Foundation trench | D 2 | 2024-03-06 | 2024-11-06 | 8 | Complete | High
| Install Foundation forms and pour foundation slab | D 3 | 2024-03-06 | 13/6/2024 | 10 | Complete | High
| Curing time for concrete | D 4 | 2024-04-06 | 2024-08-06 | 5 | Complete | High
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 20,00,000/- | 1,50,000/- | 10,000/- | 60000 | 80,000/- | 1,50,000/- | 18,50,000/-
|  | Assignee | labour charges (Per Sprint)
|  | Project Manager | 16200
|  | D 1 | 12000
|  | D 2 | 12000
|  | D 3 | 10800
|  | D 4 | 9000
|  | Total | 60000

## Sprint 2
SPRINT 2 :
| USER STORY | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY
| Measure and cut lumber for wall studs and floor joists | D 1 | 15/6/2024 | 20/6/2024 | 5 | Complete | High
| Assemble and raise wall section | D 2 | 15/6/2024 | 27/6/2024 | 11 | Complete | High
| Install floor joists and subflooring | D 3 | 18/6/2024 | 21/6/2024 | 4 | Complete | High
| Install temporary bracing for walls | D 4 | 17/6/2024 | 25/6/2024 | 8 | Not Complete | High
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 20,00,000/- | 1,20,000/- | 5,000/- | 50000 | 65,000/- | 1,20,000/- | 17,30,000/-
|  | Assignee | labour charges (Per Sprint)
|  | Project Manager | 13500
|  | D 1 | 10000
|  | D 2 | 10000
|  | D 3 | 9000
|  | D 4 | 7500
|  | Total | 50000

## sprint 3
SPRINT 3 :
| USER STORY | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| Frame the second floor walls | D 1 | 29/6/2024 | 2024-12-07 | 12 | Complete | High
| Install floor framing for the second floor | D 2 | 29/6/2024 | 2024-12-07 | 12 | Complete | High
| install roof trusses or rafters | D 3 | 2024-01-07 | 2024-09-07 | 8 | Complete | Medium
| Apply Plywood sheathing for roof deck | D 4 | 2024-01-07 | 2024-06-07 | 6 | Complete | Low
| Install temporary bracing for walls | D 4 |  |  | 2 | Complete | High | Sprint 2
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 20,00,000/- | 1,80,000/- | 10,000/- | 70000 | 1,00,000/- | 1,80,000/- | 15,50,000/-
|  | Assignee | labour charges (Per Sprint)
|  | Project Manager | 18900
|  | D 1 | 14000
|  | D 2 | 14000
|  | D 3 | 12600
|  | D 4 | 10500
|  | Total | 70000

## Sprint 4
SPRINT 4 :
| USER STORY | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| Install windows on both floors | D 1 | 2024-12-07 | 18/7/2024 | 6 | Complete | Medium
| Install exterior doors | D 2 | 15/7/2024 | 23/7/2024 | 8 | Complete | Medium
| install roof underlayment and Shingles | D 3 | 2024-12-07 | 23/7/2024 | 10 | Complete | Medium
| Inspect roofting and exterior framing | D 4 | 15/7/2024 | 18/7/2024 | 4 | Complete | Low
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 20,00,000/- | 1,40,000/- | 5,000/- | 65000 | 70,000/- | 1,40,000/- | 14,10,000/-
|  | Assignee | labour charges (Per Sprint)
|  | Project Manager | 17550
|  | D 1 | 13000
|  | D 2 | 13000
|  | D 3 | 11700
|  | D 4 | 9750
|  | Total | 65000

## Sprint 5
SPRINT 5 :
| USER STORY | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| Electrical rough-in | D 1 | 26/7/2024 | 18/7/2024 | 8 | Complete | High
| plumbing rough-in | D 2 | 26/7/2024 | 18/7/2024 | 8 | Complete | High
| Install HVAC ductwork and System Components | D 3 | 26/7/2024 | 31/7/2024 | 5 | Not Complete | Medium
| Inspect electrical, plumbing and hvac Systems | D 4 |  |  |  | Not Started | Low
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 20,00,000/- | 1,60,000/- | 10,000/- | 70000 | 80,000/- | 1,60,000/- | 12,50,000/-
|  | Assignee | labour charges (Per Sprint)
|  | Project Manager | 18900
|  | D 1 | 14000
|  | D 2 | 14000
|  | D 3 | 12600
|  | D 4 | 10500
|  | Total | 70000

## Sprint 6
SPRINT 6 :
| USER STORY | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| Install insulation in walls and celling | D 1 | 2024-09-08 | 20/8/2024 | 9 | Complete | High
| hand drywall on walls and celling | D 2 | 2024-09-08 | 22/7/2024 | 11 | Complete | High
| Finish Drywall taping, mudding, and sanding | D 3 | 2024-09-07 | 2024-10-07 | 8 | Complete | Medium
| Interior framing for any additional walls | D 4 | 2024-09-08 | 20/8/2024 | 9 | Complete | High
| Install HVAC ductwork and System Components | D 3 |  |  | 4 | Complete | Medium | Sprint 5
| Inspect electrical, plumbing and hvac Systems | D 4 |  |  | 1 | Complete | Low | Sprint 5
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 20,00,000/- | 1,30,000/- | 15,000/- | 50000 | 65,000/- | 1,30,000/- | 11,20,000/-
|  | Assignee | labour charges (Per Sprint)
|  | Project Manager | 13500
|  | D 1 | 10000
|  | D 2 | 10000
|  | D 3 | 9000
|  | D 4 | 7500
|  | Total | 50000

## Sprint 7
SPRINT 7 :
| USER STORY | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| Install exterior siding | D 1 | 23/8/2024 | 2024-03-09 | 10 | Complete | High
| Exterior planing and finishing | D 2 | 26/8/2024 | 31/7/2024 | 6 | Complete | High
| Install interior flooring | D 3 | 23/8/2024 | 2024-02-09 | 9 | Complete | Medium
| Interior Painting | D 4 | 23/8/2024 |  | 12 | Not Complete | High
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 20,00,000/- | 1,20,000/- | 5,000/- | 55000 | 60,000/- | 1,20,000/- | 10,00,000/-
|  | Assignee | labour charges (Per Sprint)
|  | Project Manager | 14850
|  | D 1 | 11000
|  | D 2 | 11000
|  | D 3 | 9900
|  | D 4 | 8250
|  | Total | 55000

## Sprint 8
SPRINT 8 :
| TASK NAME | RESPONSIBLE | START DATE | END DATE | DURATION (IN DAYS) | STATUS | PRIORITY | Orignal Sprint
| final inspection of electrical, plumbing, and HVAC | D 1 | 2024-06-09 | 2024-11-09 | 5 | Complete | Medium
| Install final appliances and fixtures | D 2 | 2024-06-09 | 2024-11-09 | 5 | Complete | Medium
| Landscaping and driveway installation | D 3 | 2024-09-09 | 17/9/2024 | 8 | Complete | Medium
| Final cleanup and Final walkthrough and handover | D 4 | 18/9/2024 | 21/9/2024 | 4 | Complete | High
| Interior Painting | D 4 |  |  |  | Complete | High | Sprint 7
| Total Budget | Sprint Budget | Miscellaneous Expense | Labour Charges | Material Expense | Total Expense | Remaining Amount
| 20,00,000/- | 1,50,000/- | 20,000/- | 60000 | 70,000/- | 1,50,000/- | 8,50,000/-
|  | Assignee | labour charges (Per Sprint)
|  | Project Manager | 16200
|  | D 1 | 12000
|  | D 2 | 12000
|  | D 3 | 10800
|  | D 4 | 9000
|  | Total | 60000